## Sheet1
Sprint 0
Hours: 10
Sprint 1
Date | Time Spent | Work Done
2025-01-22 | 3 hours | Initial Vite/React Setup
2025-01-29 | 2 hours | Setup API version call and began work on test cases
2025-02-05 | 3 hours | Setup Playwright test cases and fixed vitest test cases
2025-02-09 | 4 hours | Modularized routes
2025-02-10 | 1 hour | Began working on review and song routes
2025-02-14 | 2 hours | Planned out the next set of routes that connect to the bot
2025-02-17 | 7 hours | Setup the final database schema, and created the basic code boilerplate outline for every single route. Also created the README properly, in preparation for the end of sprint 1.
2025-02-18 | 4 hours | Working more on backend routes, setup postman tests
Sprint 2
Date | Time Spent | Work Done
2025-02-19 | 5 hours | Setting up models and repository patterns
2025-02-20 | 1 hour | Added models for objects in database
2025-02-21 | 6 hours | Added models/services and id generation, and added generic services and controllers
2025-02-21 | 2 hours | Added slug URL support
2025-02-28 | 5.5 hours | Began work on proper front end
2025-02-28 | 7 hours | Worked on Review and Song cards on front end, and making them display data
2025-03-03 | 4 hours | Switched back to using IDs, and worked more on review creation site stuff
2025-03-09 | 8 hours | Changed to small song cards and better song pages for front end
2025-03-12 | 1.5 hours | Small random fixes to front end and back end stuff
2025-03-18 | 7 hours | Started adding in Authentication with Google
2025-03-19 | 4 hours | Setup documentation and README updates, and more authentication work.